## How to lead session
1. Introduction (10 Minutes)
Provide a brief overview of the Power-Interest Grid.
Set expectations: At the end of the session, we’ll have a mapped stakeholder grid and an engagement plan.
2. Identify Stakeholders (20 Minutes)
Activity: Brainstorm all potential stakeholders involved in your contracts, teams
Use sticky notes (physical or digital) to capture each stakeholder on a separate note.
Group similar stakeholders into categories (e.g., internal, external, regulators, suppliers).
3. Categorise Stakeholders (30 Minutes)
Explain the Grid: Walk through the quadrants of the Power-Interest Grid.
Activity: For each stakeholder, assess their:
Power: Can they influence the contract/project significantly?
Interest: Are they highly impacted or engaged?
Place stakeholders into the appropriate quadrant.
Use a whiteboard or virtual collaboration tool (e.g., Miro, MURAL, Excel).
4. Develop Engagement Strategies (30 Minutes)
Discussion: For each quadrant, decide on the following:
Key communication methods (e.g., meetings, reports, dashboards).
Frequency of engagement.
Specific responsibilities for managing these stakeholders.
Document these strategies in the Notes/Actions column of the grid.
5. Review and Finalise (20 Minutes)
Summarise the grid and engagement strategies.
Assign ownership: Who will manage communication for each key stakeholder?
Set a timeline for reviewing and updating the stakeholder map.
6. Wrap-Up (10 Minutes)
Recap the outcomes of the workshop.
Share next steps: Document the grid and circulate it among participants.
Gather feedback on the session.
Workshop Tips
Use visual aids (e.g., a pre-drawn grid).
Keep the session interactive to maintain engagement.
Encourage open discussions about stakeholder dynamics and challenges.

## Info & Instructions
Quadrants of the Power-Interest Grid
More Details: https://www.projectmanagement.com/wikis/368897/stakeholder-analysis--using-the-power-interest-grid#_=_
Define Communication Plans: (You can edit these rules to suit)
| High Power, High Interest (Manage Closely) | High Power, High Interest: Weekly meetings, update regularly, shared dashboards.
| Description: Stakeholders in this quadrant require regular updates and involvement in decision-making. | High Power, Low Interest: Monthly updates and summaries.
| Examples: Senior management, key customers. | Low Power, High Interest: Email updates or newsletters.
| High Power, Low Interest (Keep Satisfied) | Low Power, Low Interest: Ad-hoc updates as needed.
Description: Stakeholders here need periodic updates to ensure they remain supportive.
Examples: Regulatory bodies, legal teams.
| Low Power, High Interest (Keep Informed) | Revisit Regularly: Stakeholder power and interest can shift over time, so update the grid periodically.
| Description: Keep these stakeholders engaged by sharing updates, as they are interested but less influential. | Tailor Engagement: Adjust your communication style and frequency based on the quadrant placement.
Examples: Team members working on contract execution, operations staff.
Low Power, Low Interest (Monitor Only)
Description: Stakeholders in this group require minimal engagement but should be monitored for any changes.
Examples: Peripheral stakeholders, third-party contractors with limited scope.

## Stakeholder List
My Stakeholders (Edit Cols to suit)
Name | Email | Contract ID | Organisation | Team/Depart | Reports to? | Power? | Interest? | Prefered Communication Style

## Power Quadrant
Last Review date: | DD/MM/YY
Stakeholder | Power | Interest | Quadrant | Notes/Actions/ Strategies/ What will I do now?
Example Stakeholder 1 | High | High | Manage Closely | Regular status updates; involve in major decisions.
Example Stakeholder 2 | High | Low | Keep Satisfied | Share periodic reports; address key concerns.
Example Stakeholder 3 | Low | High | Keep Informed | Regular communication; address queries proactively.
Example Stakeholder 4 | Low | Low | Monitor Only | Minimal engagement unless issues arise.